## Slide 1: Advanced Intelligence Surveillance POC Executive Outcome Summary
RDP LT
March 2022

## Slide 2: Agenda
Awareness
The concept is feasible using internal capability and value has been realised and early adopters interested in real world pilot and have identified more demand
Lessons Learned
Our thoughts / consideration
Sponsors Feedback & Agree Next Steps
Note: POC was delivered on time and under budget

## Slide 3: Big Thank you!
Thank you to all the individuals who helped make the project a success!
Sponsors & Business Units – RDP LT, AIA LT, GRIP and Quality Assurance for taking the risk!
RDP RMs, PP CoE and ALM
IDEA (Architecture & Environment)
AIA (Knowledge Management, Architecture & Environment)
DT Organization (EA, Aha & Sinequa)
IS Compliance (R&C)
Vendors & Partners – Sinequa, TCS, Cognizant, & Many Others

## Slide 4: Regulatory affairs value statement
POC Use Case and Learning
Enable target keyword search of limited number of regulatory agency and other websites around Medical Device topic area
Key learning from POC incorporated into core capability and use case requirements
Future Demand Identification
  Priority 1: Target keyword search of websites for regulatory agency approval of Astellas products
  Priority 2: Target keyword search of all (>100) websites article relating to Medical Device Intelligence (replace ABIS) and Regulatory Trends
  Priority 3: Target keywords search of documents – PDFs, Words, Excel, PowerPoint etc in websites
Take Away Message:
Test solution feasibility and compare solution options
Intelligence Surveillance on demand across geographies
React faster to changes
Reduced price point for data science capability
Competitive advantage
New Technology & Developments
New ways of working with IS – IS initiated Innovation
Tangible Benefits Identification
Tangible benefit worth 340 k USD per annum – net benefits subject to spend to replace capability

## Slide 5: quality assurance value statement
POC Use Case and Learning
Enable target keyword search of limited number of regulatory agency website for Quality Intelligence & Inspection Readiness Trends for GCP
Key learning from POC incorporated into core capability and use case
Future Demand Identification
  Priority 1: Target keyword search of all (>100) websites article relating to Quality Intelligence & Inspection Readiness Trends for for GCP, GMP, GVP, GLP, Supplier Quality for Drug, Medical Devices, and Combination Products topic areas
Take Away Message:
Test solution feasibility and compare solution options
Intelligence Surveillance on demand across geographies
React Faster to changes
Reduced price point for data science capability
Competitive advantage
New Technology & Developments
New ways of working with IS – IS initiated Innovation
Tangible Benefits Identification
Tangible benefit worth 100 k USD per annum – net benefits subject to spend to replace capability

## Slide 6: Platform value
Prototype solution and Feasibility Testing
Infrastructure
Definition of Solution Architecture for POC and review of solution by AIA and RDP IDEA
Prototype solution on interim server - may impact on other service – IDEA
Open Data Intelligence
Manual keyword search list
Keyword scraping of articles from simple and complex websites
Transformation of data to enable summary
Basis summary using NLP
Storage of data to enable intelligence gathering and trending
Dashboard with basic search article trending using Visualization tool
Subscription Data Intelligence (Bonus)
Keyword scraping of articles from simple and complex websites
Manual export of raw data from keyword search into solution
Take Away Message:
Test solution feasibility and compare solution options
Better branding
Understand our Customer better
Collaboration between DT, IS, AIA, RD PPP CoE and other competency
New Technology & Developments
New ways of working with our customers

## Slide 7: Lessons Learnt
No | Opportunity | Remediation Options
1 | Innovation Framework | Enterprise Innovation Framework Technical Environment Level of ceremony (R&C) Astellas Enterprise Standard
2 | Innovation Culture | Agile ways of working Showcase / awareness sessions
3 | Demand management | Single point of business accountability to champion evolution Enterprise governance (demand prioritization - business demand and other competency centers)
4 | Strategic Alignment | Executive sponsorship to champion Intersection between CSP and capability
7

## Slide 8: Enterprise innovation framework (Example)
Pilot in real world
Develop & deploy
Maintain & enhance
  Product owners to engage business and ‘own’ methodology
  Product owners with largely outsourced development
Internal capability
  Product owner with technical / IS support
POC / Protoype
External support
  Programme management
  Specialist high-end data science and/or data engineering
  External software development and programme managers
  Change management support
  Flexible support for new development and ad hoc enhancements
  Specialist / high-end data science and/or data engineering from academia and business
  Go / no-go
  Go / no-go
Input from external partners
  Specialist / high-end expertise and best practice
  Resource flexibility (scale up and down easily versus fixed internal headcount)

## Slide 9: Intelligence and Insights Surveillance (Example)
1. Web-scraping
The system collects articles and data from selected websites.
MicroService
Infrastructure (AWS) –
James Walsh
New
New
New + Existing (Sinequa)
New
2. Processing
The article text is searched for key words and summarised using Natural Language Processing.
MicroService
3. Transformation
The text collected from the articles is then transformed into a structured format (a table).
MicroService
4. Storage
The processed and transformed data is then stored in a database and filtered for different user groups.
MicroService
5. Proactive Strategy
The filtered data is then shared in checklist, emails, alerts, actionable workflows, dashboards etc.
MicroService
MA Insight
Advanced Intelligence –
RA and QA
Other POCs, Project
Using existing Astellas cloud services tenant

## Slide 10: Possible AIS approach
Foundation Components
Development Team
Priority Use Cases
Business As Usual Service
(Baseline)
Pilot in real world
Maintain & Enhance
Regulatory Use Cases
Quality Use Case
End to end use cases delivered at speed via iterative development
Foundational components necessary to enable end to end use cases delivery (MvP)
Proof of Value
Governance & Demand Management
(Baseline )
Delivery Increments
Prototype Solution
Proof of Value
Future Demand
Other Use Cases
Front End & Analytical Tools
(Baseline)
NLP
(Baseline)
Storage & Architecture Patterns (Baseline)
Business Process
(Baseline)
Delivery Increments
New Environment, Migration & SLC

## Slide 11: Take away message
Awareness
The concept is feasible using internal capability and value has been realised and early adopters interested in real world pilot and have identified more demand
Lessons Learned
Our thoughts / consideration
Agree Next Steps

## Slide 12: Appendix

## Slide 13: Phase Closeout Activities
Investment proposal & Financing for potential Next Phase
  Deliverables & Supporting documentation location
  Socialization with wider Astellas
13

## Slide 14
Prototype Lifecycle & Deliverable
Acquisition and Integration
Transformation
Enrichment & Storage
Distribution
Diverse information is acquired and integrated in real-time from a large catalogue of content sources and connectors
The information is then transformed into a normalized format
It is enriched using proprietary natural language processing (NLP)
The final stage of the Smarter Data Process focuses on delivering this information in a way which suits your organization best.
A Natural Language Processing algorithm applied to the scraped article to produce:
  A short summary of the article's introduction
  A short summary of the content within the article where the keywords were identified
The processed and transformed data stored in a database and filtered for different user groups (Intelligence Database).
Websites selected for the proof of concept
Sets of keywords are used during the scraping process to identify articles of relevance
Visualization of data
Keywords summary, Long summary, URL Links
An data science capability providing web scraping, storage, data transformation, categorisation and delivery of data through an agreed medium
The Clusters identified as being the most useful categorisations e.g. Article lists, Mixed text/documents, Research lists
Deliverables
Lifecycle
0
0
1
0
0
0
1
1
1
1

## Slide 15: POC architecture
The POC architecture demonstrates full functionality while reducing costs through the use of resources with the minimum viable performance and the removal of non-functional features such as resilience
Take Away Message:
Leveraged the best practice and approaches (AIA, DT, IDEA etc)
Astellas Data Science platform standards – Dataiku
Tableau for Visualization to speed up and plan to move to Astellas standard QlikSense in future
Compared capabilities of Sinequa platform
Actionable Workflows and Outlook exploration in next phase
Email functionality that would have summary of article – administrator account for Pinksheets – category and key sheets

## Slide 16: Agile Ways of working success
Kickoff
Sprint Delivery
JAN-22
FEB 22
Sprint 1
Project Phases
MAR 22
DEC-21
Team onboarding. Infra setup
Closure
Sprint 2
Sprint 3
Sprint 4
POC Outcome
Planning
User story refinement and prioritization.
16
Take Away Message:
We hit our delivery commitments
On Time
Under Budget
Did more than Scope
We adopted agile way of working where we defined deliverable ahead of each sprint then reviewed with the business at the end of each sprint
Delivery challenges were to do with agreements on environment to use and delay onboarding or getting commitments for competency center
With agreement from R&D, No SLC for POC which reduced documentation burden

## Slide 17: Organizational structure success
Agile Teams
Product Owner
Michael Ogbeide
Ashish Roy (PM)
Technical Team
Database SME
Naveeta
NLP Technical SME
Nikil
Front End
Naveeta
GRIP Business Team
Korina Anagnostou
Valeria Aleksandrova
RDP RMs
Support Functions
Business Sponsor
Fred Ivanow / Gary Novak
AIA
Abby
17
Quality Business Team
Harry Watson
Take Away Message:
Strong sponsorship from RDP and AIA leadership
Strong stakeholder interest and engagement from GRIP and Quality Leadership and business teams
Strong support and engagement from Aha/Sinequa, IDEA and AIA on environment
Showcase to Medical Library Services, HEOR (MA), CCP, PV, Competitive Intelligence, etc
Leveraged the same agile team to work with Global Regulatory Intelligence & Policy (GRIP) and Quality Intelligence Group
Infrastructure
Sinequa Team
IDEA SME
Brian Nigl
AIA SME
Muhammad Siddiqui
Caio Frietas Pumal
IDEA SME
Paul Batulis